## Tranches
OCBC Data Acquisition — Delivery Tranche Roadmap
Source: External: Delivery-Tranches.xlsx (distilled, not reproduced verbatim). This page captures the delivery-sequencing plan for the Cloud Sync build. It is the authoritative source for which tranche each scenario and CS-xxx story belongs to. The per-tranche scenarios map onto the components in [[reference/data-acquisition-cloud-sync-detailed-design]] and the story catalogue in [[reference/cloud-sync-user-stories]].
Sequencing principle
Each tranche is defined by a demonstrable, end-to-end scenario rather than by a component or an epic. A tranche adds the smallest coherent increment that produces a runnable, testable slice — starting from a fully-simulated Orchestrator (Tranche 1) and walking outward one real capability at a time (a real connector, then S3, then hardening, then more connectors, then the push path, then real scheduler/gateway/ops).
The tranches
Tranche | Scenario | Adds (entry → exit) | Component(s) | CS-xxx / DD IDs
1 | Request to simulated completion | Request → admission (dedupe / concurrency ceiling) → simulated task execution → cancel / resume / replay → two-phase transfer-complete callback (TRANSFER / DECOMPRESSION) → terminal state | Orchestrator only | CS-001, CS-015, CS-017, CS-018 (audit trail — every state transition written to run_event), CS-020 (simulated stub — hardened in T6a), CS-021 (simulated stub — real Worker impl in T3), CS-022, CS-026, CS-029, CS-037 (simulated stub — hardened in T6a), CS-038 (simulated stub — hardened in T6a), CS-040 (part) (resume from checkpoint, including the refusal after a validation failure; the staged-batch-removed refusal moves to T6b with CS-059), CS-041, CS-053 (simulated stub — real VALIDATE task in T3), CS-058
2 | Request to S3 (walking skeleton) | Same admission/dispatch, then a Worker claims the task, executes one real connector, writes the file to mock/local S3 (LocalStack / MinIO) via the S3 API, reports completion, and the run reaches a terminal state | Orchestrator + new Worker service | CS-006, CS-007 (part) (object read/write over the S3 API — single-part putObject to the staging zone; the ETag/version-change read check and multipart abort-on-failure move to T4), CS-009 (pass-through byte integrity), CS-019 (bounded-memory streaming — LocalFileSourceConnector enforces size pre-check; S3Uploader streams via InputStream; closed here, not re-opened in T4), CS-023 (staging zone isolation — raw/ prefix write)
3 | Request to S3, but things go wrong | Same flow, hardened: transient Worker failure → retry with backoff; classify-and-promote runs as its own task; real readiness check, manifest validation, decompression pipeline, SLA-breach detection, and JDBC/Oracle connector | Orchestrator + Worker | CS-016 (retry), CS-024 (classify+promote), CS-021 (real CHECK_READINESS — JdbcTemplate query; stub was T1), CS-011 (required manifest fields), CS-012 (batch integrity), CS-053 (real VALIDATE task — reads _manifest.json, checks CS-011/CS-012; stub was T1), CS-027 (SLA-breach detection and the no-deadline config-gap alert; moved T4→T3 2026-08-15 — alert routing is CS-043 in T6b), CS-063 (decompress landed content — stream each .gz through GZIPInputStream, re-upload without the suffix, delete the original), CS-064 (monitor the decompression component — Micrometer metrics, health indicator, idle and repeated-failure alerts), CS-004 (JDBC/Oracle relational connector), CS-008 (Parquet landing — depends on CS-004; not implemented in T2, moved here)
4 | Every source, and a clean landing | Same flow, extended to the remaining two connectors (REST/FileNet, S3-compatible/ECS) plus real decompression (remaining steps) and real validation (remaining chain members) | Worker service | Readiness & Scheduling: (CS-021 and CS-027 both moved to T3 as implemented; the readiness-poll timeout bound remains open here — see finding #16) · Connectors: CS-005 (REST/FileNet content-repository connector), CS-007 (remainder) (the S3-compatible/ECS source connector — the read side this tranche's own scenario names but which no CS-xxx previously covered — carrying CS-007's ETag/version-change exception path; plus multipart upload with AbortMultipartUpload on the write side, blocked on Q-01 file-size distribution) · Validation & Manifest Integrity: CS-054 (format/size validator — chain member), CS-055 (active-source/registration-completeness check — chain member) · Classification: CS-014 (classify batch and record destination — governance labelling before CLASSIFY_AND_PROMOTE) · Compression / Decompression Pipeline: CS-010 (compress batch before transfer — S3Compressor gzip on raw/), CS-065/CS-066/CS-067 (caller-supplied-path), CS-068 (canonical S3 key layout), CS-069 (allowlisted system IDs) · Landing: CS-070 (medallion tier routing — Bronze/Gold bucket resolved from registry at S3 write time) · Zone & Transfer Boundary: CS-025 (PUBLISH_TRANSFER_EVENT real implementation carrying source_id; the event's batch location must be the run's own prefix — …/<batchDate>/replay=<n>/ for a replay — not the batch root, or a replay's transfer points at the batch it superseded), CS-045 (part) (the IAM zone-isolation policies in docs/S3-ZONE-ISOLATION.md — DD-B10's compensating control, which must be provisioned before the transfer path can read the zone; remainder of CS-045 stays in T6b), CS-028 (outage-hold — hold at SECURED with bounded backoff; trigger mechanism still TBD) · Remaining Epic A connectors including CS-003 (uniform acquisition contract — config-driven connector factory complete when all four connectors exist)
5 | Caller pushes, not pull | Caller pushes data synchronously → admission control → direct S3 write → timeout handling | New Sync Push Service | CS-030, CS-031, CS-032, CS-033, CS-034, CS-035, CS-036, CS-056 (governance metadata consistency check — placeholder completed when Q-03 retention values resolved; T5 is the first tranche exercising the validation chain on a second mode)
6a | Real scheduler, real gateway | The Tranche 2–4 flow, triggered by a real Control-M contract and authenticated via real mTLS / Entra ID instead of the API-key stand-in | New Scheduler Job Adapter + new API Gateway | CS-020, CS-037, CS-038 (hardening — no new IDs), CS-002 (credential vaulting via CyberArk/Conjur — same class of "replace the stand-in" work as the API-key → Entra ID swap)
6b | Operator sees and reacts | Operator queries run state → resumes / replays a failed run → is alerted on SLA breach → quarantines poison batches | New Operations Service | CS-039, CS-040 (remainder) (refuse a resume once the staged batch has been removed by retention — implementable only when CS-059 can actually remove it, so it lands with the retention work), CS-042 (quarantine — deferred from T3 scope decision 2026-08-07), CS-043 (includes CS-027's alert routing — configurable severity and delivery via the observability platform, replacing the [ALERT] log stand-in), CS-044, CS-045 (remainder) (at-rest posture per D18, per-source landing segregation, and retention-driven cleanup — the zone-isolation policies moved to T4), CS-046, CS-047, CS-048, CS-049, CS-050, CS-051 (read-only pipeline config view), CS-052 (read-only run status/history view), CS-059 (zone retention enforcement — blocked on Q-03 retention values; Operations Service owns housekeeping)
7 | Business dates resolve themselves | batch_date special values (CURRENT_DATE, PREVIOUS_MONTH_END_DATE, …) → resolved to a concrete business date at run initiation using the system-wide anchor date + per-country calendars; anchor rolled forward by a scheduled Control-M job; special values pre-computed into special_value_date table by a batch job (Jollyday confined to batch only) | Orchestrator (dal-calendar library) + Sync Push Service | CS-060, CS-061, CS-062 (Epic G), CS-071 (pre-computed special_value_date table — dal-calendar reads table not runtime computation), CS-072 (special values population batch job — Jollyday confined here)
— deferred | Schema change detection + data owner verification | Not in build scope for this phase; tracked in backlog | — | CS-013 (schema change detection — BL-005; deferred 2026-07-29), CS-057 (data owner verification — BL-006; deferred 2026-07-31, WARN-only when adopted)