## Part A - Open
ID | Question | Owner | Blocks / Impact | Source | Spec coverage | Status | Notes
A2 | Production auth model. Confirm the API-key stand-in (ApiKeyAuthFilter) is replaced by Spring Cloud Gateway + Entra ID / mTLS at the gateway tier, and how operator identity is verified for resume/replay/cancel (today actingIdentity is caller-supplied and unverified). | Security / platform team | Tranche 6a (gateway); production sign-off | DD-B5; CS-037/CS-038; DD 3.2/13.4 | Target model specified (CS-037/038: token issuer/audience/expiry/entitlement, per-caller confinement, network-level internal trust). The gap is that the code still runs the stand-in - a real implementation decision, not just a value. | Open
A6 | Housekeeping / retention values (Q-03). Retention for run / run_task / run_event / push_run and each zone, satisfying 'audit retention >= zone retention + max re-run/replay latency' so the CS-015 dedup guard is never archived early. Storage decided: values live in the configuration table (per-source/per-zone, CS-059). Recommended values proposed - pending compliance sign-off (Q-03). | Data platform + compliance (sign-off) | Archival jobs; dedup-window guarantee | Detailed Design 7.2; CS-059 | Storage decided (config table, per-source/per-zone, CS-059). Values proposed: audit 90d, dedup 30d, staging & transfer-ready zones 7d, replay 30d, regulatory archive ~7yr. Pending compliance sign-off (Q-03). | Open - values proposed, pending compliance sign-off | See Analysis & Proposals sheet. Values stored in the config table (per-source). Recommended: audit 90d / dedup 30d / zones 7d / replay 30d / regulatory archive ~7yr; regulatory archival is compliance-owned and separate from the hot-store defaults.
A8 | Parquet landing (CS-008). Confirm CS-008 waits on CS-004 (JDBC/Oracle connector, Tranche 4) and the approved column type mapping (9.6.1). | DAL design owner | Tranche 4 | DD-B3; CS-008; findings #15 | Contract specified by CS-008 (Parquet output, versioned consumer-approved mapping, splitting, per-pipeline codec, not-null->required, unmapped->fail, large-object limit). Open: 9.6.1 mapping approval (Q-16) + the CS-004 connector dependency (Tranche 4). | Open | See Analysis & Proposals sheet. Depends on CS-004 (Tranche 4); core input is the approved 9.6.1 mapping (Q-16 consuming-team sign-off).
A9 | Definition-of-Done authority (finding #12). Is the 16-item dod.md or the 17-item variant (adds 'no Critical/High CVEs in a CI security scan') the canonical release gate? | Delivery lead | Release sign-off | findings #12 | Out of scope for the user stories - internal delivery-governance decision, not a spec question. | Open

## Analysis & Proposals
ID | Category | Item | Value / Detail
A6 | Storage (decided 2026-08-11) | where retention values live | In the configuration table, per-source / per-zone (CS-059), like the A3 readiness and A4 retry config. DAL owner sets the storage; the actual periods are a compliance decision (Q-03).
A6 | Recommended (compliance to sign off) | audit_retention_days (run/run_task/run_event/push_run) | 90 days (hot Postgres) - must exceed zone retention + replay window
A6 | Recommended (compliance to sign off) | dedup_window_days (CS-015) | 30 days - <= audit retention; >= longest hold (CS-028) + zone retention
A6 | Recommended (compliance to sign off) | staging_zone_retention_days | 7 days - investigate + resume window
A6 | Recommended (compliance to sign off) | transfer_ready_zone_retention_days | 7 days - investigate + replay window
A6 | Recommended (compliance to sign off) | max_replay_latency_days | 30 days - operator can replay a corrected batch within this
A6 | Recommended (compliance to sign off) | regulatory_archive_years (cold storage, separate) | ~7 years (compliance to confirm) - banking record-keeping; archived out of the hot store to the data lake / cold storage. Separate from the hot-store defaults.
A6 | Recommended (compliance to sign off) | constraint check + cleanup posture | audit 90d >= zone 7d + replay 30d = 37d OK; cleanup is fail-safe to retain - no configured value => delete nothing (CS-045/CS-059).
A8 | Analysis | Why Tranche 4 | CS-008 cannot run until the JDBC/Oracle source connector (CS-004) exists, scheduled for Tranche 4. A8 is largely a confirmation of that sequencing plus the inputs below.
A8 | Input needed | 1. Approved column-type mapping (9.6.1) - CORE | Owner: consuming app teams (Q-16 sign-off). Oracle NUMBER precision/scale -> Parquet DECIMAL; DATE/TIMESTAMP/TZ logical types; CLOB/BLOB + max-value-size (CS-019); lossless by default; unmapped type => run FAILS naming the column.
A8 | Input needed | 2. Mapping ownership + versioning | Version recorded in the manifest; changes versioned and approved by consumers.
A8 | Input needed | 3. Target Parquet file size (splitting) | Extract over target size splits into ~target-sized files, each in the manifest; per-pipeline + env default.
A8 | Input needed | 4. Compression codec | Parquet-internal per-column-chunk codec set per pipeline (CS-010); no external wrapper.
A8 | Input needed | 5. null/required + multi-table layout | not-null source column => required Parquet field, others optional; multi-table extract adds a <table_name>/ level (CS-068).
A8 | Buildable now | mechanism | Parquet writer + versioned mapping-table engine, target-size splitting, codec config, 'unmapped type => fail' guard - all parameterised. Cannot exercise end-to-end until CS-004 (Tranche 4); mapping table itself is a consuming-team contract (Q-16).